## Sheet1
Name | Duration | Start date | End date
Search for the different project ideas | 3 | 2015-05-29 | 2015-06-01
Study of the products with sample | 2 | 2015-06-02 | 2015-06-04
Prepare outline requirements | 2 | 2015-06-04 | 2015-06-06
Documentation of the project proposal | 1 | 2015-06-06 | 2015-06-07
Requirements identification analysis | 3 | 2015-06-07 | 2015-06-10
Requirements specification | 5 | 2015-06-10 | 2015-06-15
Requirements validation | 3 | 2015-06-15 | 2015-06-18
Analysis of prevailing design objects | 2 | 2015-06-18 | 2015-06-20
Architectural Design | 5 | 2015-06-20 | 2015-06-25
Data Deign | 2 | 2015-06-25 | 2015-06-27
Component Design | 2 | 2015-06-27 | 2015-06-29
Human iterface Design | 4 | 2015-06-29 | 2015-07-03
Implementation of splash screen | 1 | 2015-07-03 | 2015-07-04
Implementation of main window | 1 | 2015-07-04 | 2015-07-05
Implementation of request, simulation | 4 | 2015-07-05 | 2015-07-09
Unit testng of button presses and others | 4 | 2015-07-09 | 2015-07-13
Implementation of registration | 5 | 2015-07-13 | 2015-07-18
unit testing of regestration analysis | 6 | 2015-07-18 | 2015-07-24
Implementation of request analysis | 8 | 2015-07-24 | 2015-08-01
Unit testing of above feature | 7 | 2015-08-01 | 2015-08-08
Final integration testing and validation | 5 | 2015-08-08 | 2015-08-13